## Template
Test Category | Activity ID | X9340P DV Tasks | Predecessors | Successors | Start Date | End Date | Days | owner | design owner | Holiday | workday
DV TestBench | DV005 |  | PRD_ready | DV010 | 2021-01-20 | 2021-02-27 | 20 |  |  | 2021-02-08 | 2021-02-07
| DV010 |  | DV005 | DV015 | 2021-02-28 | 2021-03-11 | 10 |  |  | 2021-02-09 | 2021-02-20
| DV015 |  | DV010 | DV030 | 2021-03-12 | 2021-03-25 | 10 |  |  | 2021-02-10 | 2021-04-25
| DV020 |  | DV030 | DV120 | 2021-04-12 | 2021-05-10 | 20 |  |  | 2021-02-11 | 2021-05-08
| DV025 |  | RTL COMPHY ready | DV090 | 2021-03-15 | 2021-04-12 | 20 |  |  | 2021-02-12 | 2021-09-18
DV Test | DV030 |  | DV015, DE1.0 | DV035 | 2021-03-26 | 2021-04-11 | 10 |  |  | 2021-02-13 | 2021-09-26
| DV035 |  | DV030 | DV040, DV100, DV070, DV080, DV100, DV105 | 2021-04-12 | 2021-04-24 | 10 |  |  | 2021-02-14 | 2021-10-09
| DV040 |  | DV035 | DV045, DV085 | 2021-04-25 | 2021-05-24 | 20 |  |  | 2021-02-15
| DV045 |  | DV040 | DV050 | 2021-05-25 | 2021-06-22 | 20 |  |  | 2021-02-16
| DV050 |  | DV045 | DV055 | 2021-06-23 | 2021-07-20 | 20 |  |  | 2021-02-17
| DV055 |  | DV050 | DV120 | 2021-07-21 | 2021-08-17 | 20 |  |  | 2021-02-18
| DV060 |  | DV035 | DV080 | 2021-04-25 | 2021-05-24 | 20 |  |  | 2021-04-03
| DV065 |  | DV080 | DV120 | 2021-05-25 | 2021-06-22 | 20 |  |  | 2021-04-04
| DV070 |  | DV035 | DX075 | 2021-04-25 | 2021-05-24 | 20 |  |  | 2021-04-05
| DV075 |  | DV070 | DV120 | 2021-05-25 | 2021-06-22 | 20 |  |  | 2021-05-01
| DV080 |  | DV035 | DV120 | 2021-04-25 | 2021-05-24 | 20 |  |  | 2021-05-02
| DV007 |  | DV100 |  | 2021-06-08 | 2021-06-08
| DV085 |  | DV040 | DV120 | 2021-05-25 | 2021-06-22 | 20 |  |  | 2021-05-03
| DV090 |  | DV025 | DV120 | 2021-04-13 | 2021-05-11 | 20 |  |  | 2021-05-04
| DV095 |  | DV085 | DV120 | 2021-06-23 | 2021-07-20 | 20 |  |  | 2021-05-05
| DV100 |  | DV035 | DV120 | 2021-04-25 | 2021-06-07 | 30 |  |  | 2021-06-12
| DV105 |  | DV035 | DV120 | 2021-04-25 | 2021-06-07 | 30 |  |  | 2021-06-13
| DV110 |  | DV065 | DV120 | 2021-06-23 | 2021-07-20 | 20 |  |  | 2021-06-14
| DV120 |  | DV050, DV060,DV080, DV085, DV090, DV095, DV100, DV105, DV110 | DV130 | 2021-07-21 | 2021-07-27 | 5 |  |  | 2021-09-19
| DV130 |  | DV120 | FDR | 2021-07-28 | 2021-07-28 | 0 |  |  | 2021-09-20
Formulas:
End Date = IF([Days]=0, [Start Date], WORKDAY([Start Date],[Days],X2 : INDIRECT("X$"&COUNTA(X:X)) )-1 - COUNTIF(Y2 : INDIRECT("Y$"&COUNTA(Y:Y)),">"&[Start Date]) + COUNTIF(Y2:INDIRECT("Y$"&COUNTA(Y:Y)),">"&WORKDAY([Start Date],[Days],X2 : INDIRECT("X$"&COUNTA(X:X)) )-1))
Start Date = MAX(IF(IFERROR(FIND( B2:INDIRECT("B$"&COUNTA(B:B)), TRIM([Predecessors]) ),0), G2:INDIRECT("G$"&COUNTA(B:B)), 0))+1

## README
1. Please make sure that the date is written in the format 1990/1/1 . Otherwise, there will throw a warning and inform you that it may occurs an error.
2. Please enable the iterative calculation. You can find it in File-> Options -> Formulas -> Enable iterative calculation
3. You are free to add or delete Holidays, Workdays, new record by yourself
4. Please don't write any note in B column, I will regard it as a project name!!!
5. Please make sure each activity ID is not part of another activity ID. E.g. API10 is part of API100, however, API010 is not part of API100 . IF all the IDs share the same length, you won't have this trouble.
6. You can hide the holidays and workdays in formal version
7. If the predecessor is not in activity ID column, the start date will be 1990/1/0 by default. Please manually change it.